CAMPAIGN BRIEF

BFCM 2026 Sales Campaign

Smash Balloon & WPChat

| PREPARED BY Lianne Laroya | FOR Zach Tirrell and Joel Nilsson | DATE March 2026 | CAMPAIGN WINDOW Nov 18 – Dec 15, 2026 |
| --- | --- | --- | --- |

# Executive Summary

BFCM 2026 represents our biggest revenue opportunity of the year and a chance to build meaningfully on our 2025 results. This brief outlines a coordinated, early-start campaign across Smash Balloon and WPChat, covering email strategy, landing page optimization, partner outreach, new experiments, and a clear measurement framework to track progress against our 2025 baseline.

Our 2025 BFCM campaign generated $8,543.03 in Lindris-attributed email revenue, $39,879.10 in OptinMonster-attributed revenue, and $2,236.60 through partner outreach. In 2026, we are focused on three strategic shifts:

- Starting planning earlier to allow for more strategic content creation and thorough review cycles

- Expanding our channel mix with new BF-specific Lite-upgrade pages and A/B tested emails

- Recovering OptinMonster impression volume to 2024 levels — the key driver behind a 37% OM revenue drop in 2025

| 📧 $8,543 2025 email revenue (Lindris) | 🖱️ $39,879 2025 OptinMonster revenue | 🤝 $2,236 2025 partner outreach revenue | 📩 40 / 40 emails drafted & sent in 2025 |
| --- | --- | --- | --- |

# Campaign Objectives

Our 2026 BFCM campaign is built around three core objectives:

## 1. Drive Revenue Growth

- Grow Lindris-attributed email revenue beyond $8,543.03 (2025 baseline)

- Increase Lite-to-Pro conversions during the campaign window (new metric — no 2025 baseline since upgrade pages did not exist)

- Scale partner outreach revenue above $2,236.60

## 2. Improve Conversion Quality

- Address pricing page performance for WPChat with proactive CRO testing before October

- Improve email CTR and conversion rates through structured A/B testing

- Ensure every customer segment receives the most relevant offer via refined segmentation in Lindris

## 3. Establish a Repeatable Playbook

- Document all decisions, timelines, and results in a BFCM 2026 playbook to make 2027 planning even faster

- Define review and approval Service Level Agreements so the entire team is aligned during the campaign window

# Audience Segmentation

Our email campaigns will target four distinct audience segments across Smash Balloon and WPChat, each receiving tailored messaging and offers:

| Segment | Profile | Core Message | Primary CTA |
| --- | --- | --- | --- |
| Free / Lite Users | WordPress site owners using Smash Balloon or WPChat Lite. Active but not yet converted | Upgrade to Pro at our best price of the year | Lite Upgrade Page (BF theme) → Checkout |
| Existing Pro Customers | Current paying customers on single-site or multi-site plans | Upgrade your plan or add a second product at a steep discount | Upsell / All Access Bundle Page |
| Lapsed / Churned Users | Former customers or expired licenses | Come back at the lowest price we offer all year | Re-activation Offer Page |
| Organic Traffic (Cold) | New visitors arriving via blog, Google Ads, or partner referrals | Try the #1 social feed and live chat plugin for WordPress | OptinMonster campaign in blog posts → Pricing Page → Checkout |

# Channel Strategy

We will run a coordinated multi-channel campaign across owned and earned channels. The email channel remains our primary revenue driver, with supporting channels amplifying reach during the campaign window.

| Channel | Brands | 2025 Result | 2026 Focus |
| --- | --- | --- | --- |
| Email (Lindris) | Smash Balloon + WPChat | $8,543 (2025) | A/B test subject lines, CTAs, and send times; refine segmentation |
| OptinMonster | Smash Balloon + WPChat | $39,879 (2025) / $63,379 (2024) | Recover 2024 impression volume (263K vs 156K in 2025) — conversion rate held steady at ~2% both years, so volume is the only lever |
| PushEngage | Smash Balloon + WPChat | Active pushes in 2025 | Sequence: teaser → launch → last chance with progressive urgency |
| In-Plugin Notifications | Smash Balloon + WPChat | Active in 2025 | Personalize by plan type; Lite users see upgrade CTA, Pro users see bundle |
| Partner Outreach | WPChat focus | $2,236 revenue (2025) | Structured outreach to 10+ AM partners + WPBeginner roundup by Sept |

## Email Campaign Architecture

In 2025 we sent 40 emails across 7 segments.

The 2026 program builds directly on that structure with targeted improvements per segment, a new Nov 18 early access experiment for Pro users, a Nov 23 general launch following 2025’s proven Monday-before-BF playbook, and a hybrid CTA page strategy.

Total for 2026: 44 emails across an extended Nov 18 – Dec 15 window.

| Segment | 2025 Emails | 2026 Target | Key Change |
| --- | --- | --- | --- |
| Abandoned | 6 | 6 | Same structure; dates shift to match 2026 BF window + dedicated BF landing page |
| Cancelled | 3 | 5 | Dedicated BF landing page + new Nov 25 reminder + CM + GM extension |
| Basic/Plus/Elite | 11 | 12 | Early access Nov 18; Nov 23 becomes reminder; Dedicated BF landing page |
| Lite | 10 | 11 | Lite Upgrade Page as CTA throughout; Nov 25 reminder added |
| All-Access Bundle | 3 | 5 | Early access Nov 18; behavioral branching; Dedicated BF landing page + CM |
| Green Monday Pro | 3 | 2 | Tighter Dec 14–15 window + charity angle; Dedicated BF landing page |
| Green Monday Lite | 3 | 2 | Tighter Dec 14–15 window + charity + Lite Upgrade Page |
| All (Thanksgiving) | 1 | 1 | Nov 26 — same day as Thanksgiving 2026 |

## Proposed 2026 Email Sequence

The table below mirrors the 2025 spreadsheet format.

Dates are based on Black Friday = Nov 27, 2026 (Thanksgiving = Nov 26, Cyber Monday = Nov 30, Green Monday = Dec 14). ★ = New in 2026 vs. 2025 cadence.

| Send Date | Segment | Email # | Conditions | Theme | Content | Links to | Primary Creator |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Nov 18 | Basic/Plus/Elite | ★ BP1 | All Pro users | ★ Early Access ★ | Exclusive BF deal 5 days early — loyalty reward for being a Pro member | BF Landing Page (upgrade to All Access) | Lianne |
| Nov 18 | All-Access Bundle | ★ Bundle1 | All Bundle users | ★ Early Access ★ | Partner links, highlight WPChat | BF Landing Page (contains partner links, highlight WPChat) | Lianne |
| Nov 23 | Abandoned | Ab1 | All | BF Launch | Come back — our best deal of the year is live | BF Landing Page | Lianne |
| Nov 23 | Cancelled | C1 | All | BF Launch | Come back at the lowest price we offer all year | BF Landing Page | Lianne |
| Nov 23 | Lite | ★ Lite1 | All | ★ BF Launch ★ | Upgrade to Pro at our best price of the year | Lite Upgrade Page | Lianne |
| Nov 23 | Basic/Plus/Elite | ★ BP2 | Received early access Nov 18 | ★ BF Reminder ★ | Deal reminder — still live, don’t miss out | BF Landing Page (upgrade to All Access) | Lianne |
| Nov 23 | All-Access Bundle | ★ Bundle2 | Received early access Nov 18 | ★ BF Reminder ★ | Partner links, highlight WPChat | BF Landing Page (contains partner links, highlight WPChat) | Lianne |
| Nov 25 | Abandoned | Ab2 | Did NOT open Nov 23 | BF Reminder | What you’ll miss out on — deal ends this week | BF Landing Page | Lianne |
| Nov 25 | Cancelled | ★ C2 | Did NOT open Nov 23 | ★ BF Reminder ★ | Re-engagement reminder — deal closes soon | BF Landing Page | Lianne |
| Nov 25 | Lite | Lite2 | Did NOT open Nov 23 | BF Reminder | Reminder with countdown timer — upgrade offer live | Lite Upgrade Page | Lianne |
| Nov 25 | Basic/Plus/Elite | BP3 | Clicked ≥1 BF email | Partner Promo | Partner spotlight — WPForms BF deal | WPForms BF deal | Lianne |
| Nov 25 | Basic/Plus/Elite | BP4 | Did NOT open Nov 23 | BF Reminder | Reminder — deal still live, expires soon | BF Landing Page (upgrade to All Access) | Lianne |
| Nov 26 | All Segments | All1 | All users | Thanksgiving | Heartfelt message from Zach — no sale push | smashballoon.com | Lianne |
| Nov 27 | Lite | Lite3 | Clicked Nov 23 or Nov 25 | BF Cross-Sell | WPChat BF sale — get both plugins | wpchat.com/pricing | Lianne |
| Nov 27 | Basic/Plus/Elite | BP5 | Clicked any BF email | BF Cross-Sell | WPChat BF sale — get both plugins | wpchat.com/pricing | Lianne |
| Nov 28 | Basic/Plus/Elite | BP6 | Clicked ≥1 BF email | Small Business Saturday | Partner spotlight — MonsterInsights BF deal | MonsterInsights deal | Lianne |
| Nov 28 | Lite | Lite4 | Clicked ≥2 BF emails | Small Business Saturday | Partner spotlight — WP Mail SMTP BF deal | WP Mail SMTP deal | Lianne |
| Nov 28 | Abandoned | Ab3 | Did NOT open/click Nov 23 or Nov 25 | Small Business Saturday | What you’ll miss out on — ends soon | BF Landing Page | Lianne |
| Nov 28 | Lite | Lite5 | Did NOT open/click any email after Nov 23 | Small Business Saturday | Reminder with countdown timer — ends soon | Lite Upgrade Page | Lianne |
| Nov 28 | Basic/Plus/Elite | BP7 | Did NOT open Nov 23 or Nov 25 | BF Reminder | Reminder — deal closing soon | BF Landing Page | Lianne |
| Nov 28 (Sat) | Basic/Plus/Elite | ★ BP8 | All | ★ SBS Extended ★ | Small Biz Sat: extended value + All-Access Bundle highlight | BF Landing Page | Lianne |
| Nov 28 (Sat) | Lite | ★ Lite6 | All | ★ SBS Extended ★ | Small Biz Sat: extended deal — still time to upgrade | Lite Upgrade Page | Lianne |
| Nov 28 (Sat) | All-Access Bundle | Bundle3 | All | SBS Extended | Small Biz Sat: All-Access Bundle deal extended through weekend | BF Landing Page | Lianne |
| Nov 29 | Abandoned | Ab4 | All | BF Ending Soon | Last chance — sale ends tonight (countdown timer) | BF Landing Page | Lianne |
| Nov 29 | Basic/Plus/Elite | BP9 | Did NOT open SBS email | BF Ending Today | Ending Today (countdown timer) | BF Landing Page | Lianne |
| Nov 29 | Lite | Lite7 | Did NOT click any BF email in 6 days | BF Ending Today | Ending Today (countdown timer) | Lite Upgrade Page | Lianne |
| Nov 30 (CM) | Abandoned | Ab5 | All | CM Launch | Cyber Monday sale — even bigger savings | BF Landing Page | Lianne |
| Nov 30 (CM) | Cancelled | C3 | All | CM Launch | Cyber Monday re-engagement offer | BF Landing Page | Lianne |
| Nov 30 (CM) | Basic/Plus/Elite | BP10 | All | CM Launch | Cyber Monday — All-Access Bundle deal | BF Landing Page | Lianne |
| Nov 30 (CM) | Lite | ★ Lite8 | All | ★ CM Launch ★ | Cyber Monday — upgrade to Pro today | Lite Upgrade Page | Lianne |
| Nov 30 (CM) | All-Access Bundle | ★ Bundle4 | All | ★ CM Launch ★ | Partner links, highlight WPChat | BF Landing Page (partner links, WPC) | Lianne |
| Dec 2 | Abandoned | Ab6 | Did NOT click CM launch | CM Extended | Extended ‘til Friday — don’t miss out | BF Landing Page | Lianne |
| Dec 2 | Cancelled | C4 | Did NOT click CM launch | CM Extended | Extended ‘til Friday — last chance to come back | BF Landing Page | Lianne |
| Dec 2 | Basic/Plus/Elite | BP11 | Did NOT click CM launch | CM Extended | Extended ‘til Friday — CM deal still live | BF Landing Page | Lianne |
| Dec 2 | Lite | Lite9 | Did NOT click CM launch | CM Extended | Extended ‘til Friday — upgrade offer still live | Lite Upgrade Page | Lianne |
| Dec 4 | Basic/Plus/Elite | BP12 | Did NOT open/click CM emails | CM Ending Today | Ending Today + WPChat cross-sell | BF Landing Page | Lianne |
| Dec 4 | Lite | Lite10 | Did NOT open/click CM emails | CM Ending Today | Ending Today (countdown timer) | Lite Upgrade Page | Lianne |
| Dec 4 | Cancelled | ★ C5 | Did NOT click any email after BF launch | ★ CM Final Push ★ | Last chance re-engagement — this is it | BF Landing Page | Lianne |
| Dec 4 | All-Access Bundle | ★ Bundle5 | Did NOT open/click CM emails | ★ CM Ending Today ★ | CM ending — last chance for All-Access Bundle | BF Landing Page | Lianne |
| Dec 4 | Lite | ★ Lite11 | Opened CM launch but did NOT convert | ★ CM Cross-Sell ★ | WPChat Cyber Monday deal — get both plugins | wpchat.com/pricing | Lianne |
| Dec 14 (GM) | Basic/Plus/Elite | ★ GMPro1 | All | ★ Green Monday ★ | Sale + charity partner spotlight — give back while saving | BF Landing Page | Lianne |
| Dec 14 (GM) | Lite | ★ GMLite1 | All | ★ Green Monday ★ | Sale + charity angle + upgrade message | Lite Upgrade Page | Lianne |
| Dec 15 | Basic/Plus/Elite | ★ GMPro2 | Did NOT click Dec 14 launch | ★ GM Ending Today ★ | Ending Today — last chance of the season | BF Landing Page | Lianne |
| Dec 15 | Lite | ★ GMLite2 | All | ★ GM Ending Today ★ | Ending Today — last chance to upgrade | Lite Upgrade Page | Lianne |

★ = New in 2026 vs. 2025 cadence     Total emails: 44 (up from 40 in 2025)

## Key Improvements vs. 2025

- Nov 18 early access to Pro users (BPE + Bundle) — 5 days before the general launch on Nov 23. New experiment to reward loyalty and drive early revenue before the peak window.

- A/B test on this email: urgency subject line vs. status subject line (“You’re getting it first”)

- Nov 23 general launch follows 2025’s proven playbook (Monday before BF) for Lite, Abandoned, and Cancelled segments. BPE + Bundle receive a reminder email on Nov 23 instead, since they already got the deal Nov 18.

- Nov 25 Wednesday reminders added — following the same Mon-launch → Wed-reminder pattern from 2025. Covers non-clickers of the Nov 23 launch across all segments.

- Hybrid CTA page strategy — Lite Upgrade Page for Lite segment, dedicated BF landing page for all others.

- Reasoning: In 2024 we used a dedicated BF landing page and performance was strong. In 2025 we sent to the generic pricing page and email revenue was lower.

- CRO best practice is message match: a subscriber who clicks “get your Black Friday deal” expects to land on a page that reinforces that context. A generic pricing page breaks that continuity and increases bounce.

- For Lite users specifically, the Lite Upgrade Page is even stronger because it’s personalized to their current plan and shows the exact upgrade path.

- Requires dev work to build the BF landing page — see Decisions Needed.

- Cyber Monday 2026 = Nov 30 (Monday after Thanksgiving Nov 26). All CM emails shift accordingly; CM extended = Dec 2, CM ending = Dec 4 (Friday).

- Green Monday moves to Dec 14–15 — the actual Green Monday 2026 date (second Monday of December). Tighter 2-day window vs. 2025’s 5-day run; adds a charity partner angle to differentiate it from BF/CM.

- Cancelled segment strengthened: 3 → 5 emails, adding Nov 25 reminder and Cyber Monday final push.

- Partner promos remain gated to high-engagement users (1+ or 2+ clicks) to protect list quality and maximize relevance.

# Key Experiments for 2026

With a full campaign cycle of experience to build from, we are introducing four structured experiments this year. Each has a clear hypothesis, test mechanism, and success metric so we can make data-driven decisions for 2027.

| Experiment | What We Test | Success Metric |
| --- | --- | --- |
| Email A/B Testing | Subject line formulas (urgency vs. value vs. curiosity), CTA button copy, preview text, and send time | Lift in open rate and CTR vs. 2025 per-email averages |
| Lite Upgrade Pages | Dedicated Lite-to-Pro upgrade landing pages for both Smash Balloon and WPChat with BFCM-specific overlays | Lite-to-Pro conversion rate during BFCM window (new baseline) |
| Pricing Page CRO | A/B test layout, social proof placement, pricing anchoring, and CTA variants on the WPChat pricing page | Pricing page conversion rate vs. BFCM 2025 |

## Partner Outreach Program

In 2025, partner placements generated $2,236.60 with minimal structure. In 2026, we will build this into a systematic program:

- Build a master outreach list of 10+ AM ecosystem partners (WPForms, MonsterInsights, WPBeginner, etc.) by June

- Contact each partner with a co-promotion proposal by July, well ahead of their own BFCM planning cycles

- Track each placement with unique UTM parameters to attribute revenue per partner

- Target: $4,000+ in partner-attributed revenue (2x 2025)

# Campaign Timeline

By moving planning significantly earlier, we are building in adequate review time at every stage and avoiding last-minute production pressure.

| Phase | Timeline | Key Deliverables |
| --- | --- | --- |
| Strategy Lock | March – April 2026 | Finalize discount structures, offer tiers, Green Monday charity partner and channel plan. Align with Joel + Zach. |
| Asset Development | May – July 2026 | Build Lite upgrade pages (BF theme), run pricing page CRO tests, initiate partner outreach, begin landing page design for BFCM-specific variants. |
| Content Creation | August – September 2026 | Draft all email copy (target: 44 emails). Confirm list of partners and draft emails for partners. |
| Review & QA | October 2026 | Full email review cycle with Joel. Lindris segment validation and pre-send QA. Landing page BFCM variants live in staging. All assets approved. |
| Campaign Launch | Nov 18 – 27, 2026 | Nov 18: Early access email to Pro users (BPE + Bundle). Nov 23: General BF launch (Lite, Abandoned, Cancelled) + BPE/Bundle reminder. Nov 25: Wednesday reminders. Nov 26: Thanksgiving. Nov 27: Black Friday behavioral sends begin. |
| BFCM Core Window | Nov 27 – Dec 4, 2026 | Full campaign active across all channels. Daily Lindris check-ins. Cyber Monday Nov 30. CM Extended Dec 2. Final CM sends Dec 4. Real-time monitoring and pivots throughout. |
| Extension: Green Monday | Dec 14 – 15, 2026 | Green Monday launches on Dec 14 (BPE + Lite) with charity partner angle. Ending Today sends Dec 15 for non-clickers. |
| Debrief & Playbook | December 2026 | Full campaign performance report vs. 2025 baseline. Document wins, learnings, and recommendations. Publish BFCM 2027 starting brief. |

# Success Metrics

Metrics are tracked across three channels: email (Lindris + GA4), OptinMonster, and partner outreach. The combined 2025 baseline across all three is approximately $50,659. The 2026 goal is to meaningfully grow total campaign revenue, with OM impression recovery being the single highest-leverage opportunity.

| Metric | 2025 Baseline | 2026 Target | Owner | Priority |
| --- | --- | --- | --- | --- |
| Email Revenue (Lindris) | $8,543.03 | > $11,000 (+29%) | Lianne | P0 |
| Email Revenue (GA4) | $5,454.29 | > $7,500 (+38%) | Lianne | P0 |
| OM Revenue (smashballoon.com) | $39,879.10 (2025) / $63,378.92 (2024) | > $45,000 | Lianne + Aman | P0 |
| OM Impressions | 156,684 (2025) / 263,208 (2024) | > 200,000 | Lianne + Aman | P0 |
| OM Conversion Rate | 2.01% (2025) / 1.97% (2024) | Maintain ~2%+ | Lianne + Aman | P1 |
| Partner Revenue | $2,236.60 | > $4,000 (+79%) | Lianne | P0 |
| Pricing Page Conv. Rate | Baseline TBD (Aug test) | Beat baseline by 10%+ | Lianne + Aman + Dev | P0 |
| Lite-to-Pro Conversions | None (new metric) | Establish Year 1 baseline | Lianne + Aman + Dev | P1 |
| Email A/B Test Wins | No tests in 2025 | 3+ documented wins | Lianne | P1 |
| Total Emails Drafted | 40 / 40 | 44 / 44 | Lianne | P1 |

Key insight — OptinMonster:

The OM conversion rate held steady at ~2% in both 2024 (1.97%) and 2025 (2.01%), which tells us the popup experience, offer, and targeting are all working.

The $23,500 revenue gap is entirely an impressions problem: 263K impressions in 2024 vs. 156K in 2025, a 40% drop.

At a stable 2% conversion rate and ~$12 average order, every 10,000 impressions recovered = roughly $2,400 in OM revenue.

The impression drop traces back to declining organic search traffic. AI Overviews are answering informational queries (how-tos, comparisons, roundups) directly in Google, reducing click-throughs to the site even when rankings hold. This is a structural shift.

For 2026, recovering OM impressions means shifting traffic strategy toward channels AI Overview can't touch:

- Paid search on branded + transactional queries during the BFCM window ("Smash Balloon Black Friday deal") - high purchase intent, AI Overview rarely appears on commercial queries

- Partner placements - referral traffic from WPBeginner, WPForms, MonsterInsights arrives with buying intent and no suppression cookies

- Email click-throughs - every link click from the 45-email sequence is a direct site visit and a potential OM impression

- Paid retargeting on Meta/Google Display - re-engage past visitors during the 3-week window

Notes on attribution:

- Primary email metric: Lindris-attributed revenue (most complete view of email performance)

- OM revenue: OptinMonster dashboard attribution (smashballoon.com); tracked separately from email

- Partner revenue: tracked via UTM parameters per partner placement

# Decisions Needed from Leadership

To move forward with the strategy and timeline above, we need alignment on the following by end of April 2026:

| Decision | Options | Owner |
| --- | --- | --- |
| Discount structure for BFCM 2026 | % off vs. fixed pricing vs. bundle deal | Zach + Joel |
| Build a dedicated BF landing page? | Recommended: Yes — reverting to 2024 approach. Requires dev work by Oct. Lite segment will point to Lite Upgrade Page instead. | Zach + Joel + Lianne + Aman + Dev |
| Green Monday charity partner | Select partner org by April for Dec 14–15 campaign | Zach + Joel |
| Pricing page CRO A/B test | Confirm dev availability to run WPChat pricing page test May–Aug | Joel + Lianne + Dev |

Questions or feedback? Reach out to Lianne Laroya via Slack or email

llaroya@awesomemotive.com